## Sheet1
Thames Protection and Resilience Project |  | 2024-02-14
DRAFT PROJECT PLAN
Activities | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Council Meetings | bar: 2024-03-01; 2024-06-01; 2024-09-01
|  | Leadership team | [6 empty] | Adoption by Council
Governance Meetings | 2024-02-01: Governance meeting #1; 2024-03-01: Joint Governance meeting; 2024-06-01: Governance meeting #3; 2024-08-01: Governance meeting #4
Project Team Meetings | 2024-02-01: 2024-02-20; 2024-03-01: (#2) with Project Team (#1); 2024-05-01: PT meeting #2; 2024-06-01: PT meeting #3; 2024-07-01: PT meeting #4; 2024-08-01: PT meeting #5
Agenda items | 2024-02-01: 1 Background 1a SMP protection 1b Spatial planning 2 Terms of reference and project structure 3 Programme overview 4 Stakeholder mapping and design principles; 2024-03-01: 1 Marae visit 2 Site walkover 3 SLR update 4 Design process overview 5 Design philosophy agreed; 2024-05-01: Baseline modelling outputs Draft design WRC flood protection role; 2024-06-01: Protection cost estimates Development opportunities Managed retreat locations; 2024-07-01: Planning requirements Spatial Plan Business Case (Thames); 2024-08-01: Recommended protection scheme Recommended plan change actions Spatial planning priorities
Inputs | 2024-02-01: Scope presentation TOR Project structure diagram Draft programme; 2024-03-01: Basis of design (BoD) Design presentation; 2024-05-01: Modelling and design presentations Presentation from WRC; 2024-06-01: Cost estimates Spatial plan outcomes; 2024-07-01: Draft Spatial Plan Draft Business Case
Tasks (not covered below) | 2024-01-01: Draft programme Discuss design philosophy (see BoD); 2024-02-01: Stakeholder mapping materials; 2024-03-01: Site visit preparation Consider enhancement opportunities; 2024-04-01: Draft Newsletter Public meeting preparations; 2024-05-01: Define development opportunities and retreat locations; 2024-06-01: Define development opportunities and retreat locations; 2024-07-01: Define planning requirements Draft Newsletter Public meeting preparations; 2024-08-01: Define plan change actions and priorities Consider funding streams
Concept Design | bar: 2024-01-01 to 2024-08-01
Basis of design (BoD) confirmation | bar: 2024-01-01 to 2024-03-01
Calculations | bar: 2024-04-01
Initial drafting and QS | bar: 2024-05-01
Refinement based on modelling outputs | bar: 2024-06-01
Reporting | bar: 2024-07-01
Finalise design | bar: 2024-08-01
Tuflow modelling | bar: 2024-01-01 to 2024-06-01
Data collation and survey specification | bar: 2024-01-01
Survey | bar: 2024-01-01 to 2024-02-01
Model build | bar: 2024-02-01 to 2024-03-01
Model calibration | bar: 2024-03-01 to 2024-04-01
Baseline mapping & option development | bar: 2024-04-01 to 2024-05-01
Option modelling | bar: 2024-05-01 to 2024-06-01
Reporting | bar: 2024-06-01 to 2024-07-01
Peer Review?
Business Case | bar: 2024-01-01 to 2024-09-01
Develop framework & define inputs | bar: 2024-01-01 to 2024-02-01
Drafting - Coromandel | bar: 2024-02-01 to 2024-05-01
Drafting - Thames | bar: 2024-04-01 to 2024-06-01
Programme of works/cost estimates overtime | bar: 2024-06-01 to 2024-07-01
Reporting | bar: 2024-07-01 to 2024-09-01
Thames Spatial Plan | bar: 2024-01-01 to 2024-09-01
Public engagement | 2024-03-01: Project introduction -targeted stakeholders; 2024-05-01: Newsletter - targeted stakeholders Public meeting; 2024-07-01: Newsletter - targeted stakeholders Public meeting; 2024-09-01: Seek funding based on Business Case